## 1st WEEK
CALORIE AMORTIZATION SCHEDULE
| PASSERELLES NUMERIQUES of CAMBODIA |  |  | TUTOR : - Rady - Sokhom | STUDENT NAME: SokkunNorn
| DATE | TIME | WORK ACTIVITIES | DIFFICULTIES/ISSUES | STATUS | PLAN TO COMPLETE | SOLUTIONS | WHAT DID YOU LEARN? | COMMENT | % OF GOAL
| 2019-04-02 | 1:00pm - 2:00pm | Get topic IT reseach. | I don’t know about program language React and cofuse with language React Native. | HOLD | I need to understand about what is React first. | I need to watch youtube and search some website about React. | I learn some information from React. | Nothing | #REF!
| 2019-05-02 | 11:00pm - 12:30am | Research youtube. | I have problem with listening Englist language on youtube | DONE | I try to find definition of React | Ask my friends and watch youtube. | I learn about listening and more searching. | Nothing
| 2019-06-02 | 11:30pm - 12:00am | Read document on website. | It has a lot of keywords that I need to understand. | HOLD | I need to know about history of React. | Watch youtube and read on document. | I get more skill reading and searching. | Nothing
| 2019-07-02 | 10:00pm - 11:00pm | Watch how to write code on youtube | I never know structure code before | HOLD | I want to know structure and how to write code. | I try to execute code step by step | I know some component on structure code React. | Nothing
| 2019-08-02 | 12:00am - 1:30am | Research youtube and read document. | I try to understand code again and again | HOLD | I want to know structure and how to write code. | I try to execute code step by step | I understand some code in React. | Nothing
| 2019-09-02 | 1:30pm - 4:00pm | Write simple code. | Error code a lot. | DONE | I try to show result on broswer. | Excecute code again and read document. | I learn how to the stracture code. | Nothing
| 2019-10-02 | 8:30am - 12:00pm | Write simple code again. | Have some error code. | DONE | Complete the result code. | Read document and try to understand code. | I understand some code in React. | Nothing
REFLECTION
In summary a week ago I get understanding about react language, can write some about React language and I can do rearching a lot from youtube and some website that have document about react language.
WEEKLY WORK LOG

## 2nd WEEK
CALORIE AMORTIZATION SCHEDULE
| PASSERELLES NUMERIQUES of CAMBODIA |  |  | TUTOR : - Rady - Sokhom | STUDENT NAME: SokkunNorn
| DATE | TIME | WORK ACTIVITIES | DIFFICULTIES/ISSUES | STATUS | PLAN TO COMPLETE | SOLUTIONS | WHAT DID YOU LEARN? | COMMENT | % OF GOAL
| 2019-11-02 | 7:00pm - 9:00pm | Think about web application |  | HOLD |  |  |  |  | #REF!
| 2019-12-02 | 7:00pm - 9:00pm |  |  | HOLD
| 13/2/2019 | 7:00pm - 9:00pm |  |  | HOLD
| 14/2/2019 | 7:00pm - 9:00pm |  |  | HOLD
| 15/2/2019 | 7:00pm - 9:00pm |  |  | HOLD
| 16/2/2019 | 7:00pm - 9:00pm |  |  | HOLD
| 17/2/2019 | 7:00am - 11:00am |  |  | HOLD
REFLECTION
WEEKLY WORK LOG

## 3rd WEEK
CALORIE AMORTIZATION SCHEDULE
| PASSERELLES NUMERIQUES of CAMBODIA |  |  | TUTOR : - Rady - Sokhom | STUDENT NAME: SokkunNorn
| DATE | TIME | WORK ACTIVITIES | DIFFICULTIES/ISSUES | STATUS | PLAN TO COMPLETE | SOLUTIONS | WHAT DID YOU LEARN? | COMMENT | % OF GOAL
| 18/2/2019 | N/A | [7 empty] | #REF!
| 19/2/2019 | 10:00am - 11:30am | Update wep application | find check list and footer | DONE | create list with from ckeck box for easy to user check it done or not | search from bootstrap 4 | find new idea from bootstrap mix between ul and form check box | nothing
| 20/2/2019 | N/A
| 21/2/2019 | N/A
| 22/2/2019 | N/A
| 23/2/2019 | N/A
| 24/2/2019 | N/A
REFLECTION
In this week I have a little time for searching react but I found new idea to update my web application is easy to user for checking their are complite or not. In need week I want to update my web application about dropdown in task when user check their task are done because i think that dropdown in task can make my web application more usefull user. It is not messi in their task.
WEEKLY WORK LOG

## 4th WEEK
CALORIE AMORTIZATION SCHEDULE
| PASSERELLES NUMERIQUES of CAMBODIA |  |  | TUTOR : - Rady - Sokhom | STUDENT NAME: SokkunNorn
| DATE | TIME | WORK ACTIVITIES | DIFFICULTIES/ISSUES | STATUS | PLAN TO COMPLETE | SOLUTIONS | WHAT DID YOU LEARN? | COMMENT | % OF GOAL
| 25.2.2019 | N/A | [7 empty] | #REF!
| 26.2.2019 | N/A
| 27,2,2019 | N/A
| 28,2,2019 | N/A
| 1.3.2019 | 8:00pm - 9:00pm | search on youtube | It has a lot of video tutorial but some tutorial is not start from sratch | HOLD | research on youtube for dropdown list todo in my wep application. | search youtube on page codelife about react dropdown list todo. | Improve searching and find new page video tutorial. | nothing
| 2.3.2019 | N/A
| 3.3.2019 | N/A
REFLECTION
In this week, I cannot do anything a lot about react language because I have midterm but I try to search some information that I need to do in next week. I think that in next week I can complete my project. I hope that I con do dropdown list todo in my project.
WEEKLY WORK LOG

## 5th WEEK
CALORIE AMORTIZATION SCHEDULE
| PASSERELLES NUMERIQUES of CAMBODIA |  |  | TUTOR : - Rady - Sokhom | STUDENT NAME: SokkunNorn
| DATE | TIME | WORK ACTIVITIES | DIFFICULTIES/ISSUES | STATUS | PLAN TO COMPLETE | SOLUTIONS | WHAT DID YOU LEARN? | COMMENT | % OF GOAL
| 2019-04-03 | N/A | [7 empty] | #REF!
| 2019-05-03 | N/A
| 2019-06-03 | N/A
| 2019-07-03 | N/A
| 2019-08-03 | N/A
| 2019-09-03 | 10:00 am - 11:30am | seach dropdown list | some codes are diffecult to understand | HOLD | seach dropdown list to make it more easy when user want to delete their task | read document on website and search on youtube. | I get more knowledge from reading document on website | nothing
| 2019-10-03 | N/A
REFLECTION
In this week, I spended short time for researching on my project but I try to do step by step to be success on my project.
About my project, I got result about 75% for complete it. I hope that I will build it on time.
Next week, I will try to do dropdown list to do from my searching on website and some video.
WEEKLY WORK LOG

## 6th WEEK
CALORIE AMORTIZATION SCHEDULE
| PASSERELLES NUMERIQUES of CAMBODIA |  |  | TUTOR : - Rady - Sokhom | STUDENT NAME: SokkunNorn
| DATE | TIME | WORK ACTIVITIES | DIFFICULTIES/ISSUES | STATUS | PLAN TO COMPLETE | SOLUTIONS | WHAT DID YOU LEARN? | COMMENT | % OF GOAL
| 2019-10-04 | N/A | [7 empty] | #REF!
| 2019-10-03 | N/A
| 2019-10-03 | N/A
| 2019-10-03 | N/A
| 2019-10-03 | N/A
| 2019-10-03 | 1:00 pm - 5:00 pm | drop down list | find script dropdown list to do | DONE | try to delete list user created | mix with script alert bootstrap | I think that drop down lists are difficul but finally, it's done when I am just input alert bootstrap. | no comment
| 2019-10-03 | N/A
REFLECTION
This week, I am very grade when I complete my task is a drop-down list. My subject gets maybe 80% I will finish it soon when I have free time. In next week I have some feature to update my project from technical teacher's feedback. I hope that next week, I can finish my task and make it better for my application.
WEEKLY WORK LOG
WEEKLY WORK LOG

## 7th WEEK
CALORIE AMORTIZATION SCHEDULE
| PASSERELLES NUMERIQUES of CAMBODIA |  |  | TUTOR : - Rady - Sokhom | STUDENT NAME: SokkunNorn
| DATE | TIME | WORK ACTIVITIES | DIFFICULTIES/ISSUES | STATUS | PLAN TO COMPLETE | SOLUTIONS | WHAT DID YOU LEARN? | COMMENT | % OF GOAL
| 18/3/2019 | N/A | [7 empty] | #REF!
| 19/3/2019 | N/A
| 20/3/2019 | N/A
| 21/3/2019 | N/A
| 22/3/2019 | N/A
| 23/3/2019 | 8:00am - 11:00am | search plugin drag drop | have a lot of plugin but some plugin don’t have document for reading | HOLD | search plugin for using drag drop task for getting more easy to user use it. | go to website for find plugin drag and drop | find new plugin for using specific feature to update my application more easy to use. | nothing
| 24/3/2019 | N/A
REFLECTION
In this week I spand a short time for my IT reseach but I think that my application will be done.
I need to write document about drag and drop plugin JavaScript for getting result drag and drop application Task Management.
I have some problem with plugin because it need to read document but I think everything will be done.
I think that next week, I will do it well before deadline.
WEEKLY WORK LOG

## 8th WEEK
CALORIE AMORTIZATION SCHEDULE
| PASSERELLES NUMERIQUES of CAMBODIA |  |  | TUTOR : - Rady - Sokhom | STUDENT NAME: SokkunNORN
| DATE | TIME | WORK ACTIVITIES | DIFFICULTIES/ISSUES | STATUS | PLAN TO COMPLETE | SOLUTIONS | WHAT DID YOU LEARN? | COMMENT | % OF GOAL
| 25/3/2019 | N/A | [7 empty] | #REF!
| 26/3/2019 | 7:00 pm - 9:00 pm | use drag and drop plugin | plugin work with element html only | NOT DONE | drag and drop each list task for user | stop to use plugin drag and drop. | search and know some type of plugin drag and drop | nothing
| 27/3/2019 | N/A
| 28/3/2019 | N/A
| 29/3/2019 | N/A
| 30/3/2019 | N/A
| 31/3/2019 | N/A
REFLECTION
This week, I cannot complete my task. I can build my application by 80% only. I am very regrated for drag and drop on each task, but I can do my research for building application. Moreover, I will learn about React because in IT sector, react is most populate for the mobile app so, I think can learn to React is better for building a mobile application.
WEEKLY WORK LOG

## Sheet1 (hidden)
DONE
HOLD
NOT DONE

## Exercise Type Lookup (hidden)
Exercise Type Lookup
This sheet should remain hidden.
EXERCISE TYPE | DESCRIPTION | FACTOR
SEDENTARY | LITTLE TO NO EXERCISE | 1.2
LIGHT ACTIVITY | EXERCISE 1-2 DAYS/WEEK | 1.375
MODERATE ACTIVITY | EXERCISE 3-5 DAYS/WEEK | 1.55
VERY ACTIVE | EXERCISE 6-7 DAYS/WEEK | 1.725
EXTRA ACTIVE | EXERCISE 6-7 DAYS/WEEK + PHYSICAL JOB/2X TRAINING | 1.9